Strengthening Public Financial Management of the Government of Nepal

Results Chain for the Nepal MultiDonor Trust Fund (MDTF)

May 2013

Nepal Public Financial Management (PFM) Multi Donor Trust Fund

Results Framework for period 2011-2015

May 2013

| Results Chain | Performance Indicators | Definition& Data Source |
| --- | --- | --- |
| Impact: A Nepal that is prosperous, peaceful and just. Aligned with the Nepal PFMRP Results to which the MDTF can contribute in the long run | Poverty reduction as measured by MDG targets. | Aligned with PFMRP |
|  | Vulnerable and marginalized people accessing entitlements more often and on a regular basis. | Aligned with PFMRP |
|  | Increased investment in Nepal by both public and private sectors. | Baseline: 5.2% of GDP in FY10 |
|  | Increased channeling of donor assistance through government systems. | Baseline: 2010 62% of donor aid flows use country PFM systems. 2011 35% use country procurement systems |
|  | Government allocating resources based on needs/priorities. | Budget allocations based on two-year GoN strategic plans. |
| Outcome: Government of Nepal demonstrating improved governance, optimizing outputs from public resources and facilitating inclusive and broad-based development at scale. Aligned with the Nepal PFMRP Results to which the MDTF can contribute in the long run | Bunching of capital expenditures in the last trimester reduced from 70% in 2012 to 60% in 2015. | Baseline: 70% Target: 60% Budget allocation and expenditure tracking. |
|  | Information on budget allocation and expenditure in 3 sectors made public 3 times a year by 2015. | Baseline: 0 Target: 3 sector ministries 3 times/year Data collected by social accountability grantees through pro-poor budget analyses. |
|  | Nepal CPIA rating on quality of budgetary and financial management improves from 2.5 in 2011 by EOP. | Baseline: 2.5 in 2011 Target: improvement in CIPA rating |
|  | At least 2 Ministries running major entitlement programs undertake reform actions as a result of SA work by June 2015. | Baseline: 0 Target: 2 Data collected through social audits, done by national-level grantees |
|  | 90 VDCs and 15 District governments taking up reform recommendations proposed from local Social Accountability work by June 2015. | Baseline: 0 Target: 90 VDCs and 15 districts to pick up at least 1 recommendation |
| Intermediate Outcome: Financial transparency, performance and accountability of Public Financial Management (PFM) improved at the National and Local levels in Nepal. | 98% of overall budget executed through the DTCOs, where the TSA system has been implemented by June 2015. | Baseline: 7% Target: 98% Data Source: TSA reports |
|  | 100% of budget execution reports and financial statements (meeting acceptable standards of quality, completeness and timeliness) prepared by FCGO using TSA system by June 2015. | Baseline: 0 Target: 100% Data Source: FCGO Budget reports |
|  | 50% of current year audit recommendations implemented within one year by June 2015. | Baseline: Less than 35% Data Source: OAG Records/Annual Report |
|  | PFM is covered in radio programs and print articles at least 20 times as a result of national social accountability work by June 2015. | Baseline: N/A Target: 20 |
|  | Within the 90 VDCs targeted, at least 75% of the VDCs show 10% increase of entitlements being disbursed to the correct beneficiaries, on time and of the correct amount by June 2015. | Baseline: 0 Target: 75% Data Source: District office registries to be reviewed by local level grantees |
| Output 1:Systems Development & Capacity Building Public Financial Management (PFM) systems and capacities strengthened. | Treasury Single Account (TSA) implemented in 60 districts by July 2012 and in all 75 districts by July 2013. | Baseline: 8 DTCOs Target: 75 |
|  | Nepalese Financial Reporting Standards (NFRSs) drafted in line with International Financial Reporting Standards (IFRSs) and issued by ICAN by June 2015. | Baseline: 0 Target: Standards drafted |
|  | Spending Unit Bank Accounts reduced by 75% by June 2015. | Baseline: 14,000 bank accounts Target: At least 75% reduction |
|  | Repeater PEFA study and 4 additional research studies completed and findings reports disseminated using various means (passive and active) by June 2015. | Baseline: 1 PEFA study Target: 5 studies Data source: Study papers |
|  | Programs to raise awareness of GoN financial management staff on PFM reforms carried out in 75% of all districts in Nepal by June 2015. | Baseline: 0 Target: 75% of Districts Data source: Session agenda, attendance records |
| Output 2: Audit Enhancement Quality of public sector audits enhanced. | Percentage of financial statement audits substantially meeting OAG auditing standards increased from 35% in 2011 to 60% by June 2015. | Baseline: 35% Target 60% Data Source: Quality assurance team records |
|  | Frequency of in-depth performance audit reports increased from 1 per year in 2012 to 3 per year by June 2015. | Baseline: 1 audit/yr Target: 3 audits/yr by 2015 Data Source: OAG Nepal website |
| Output 3: Social Accountability Mechanisms Mechanisms to engage citizens in PFM reform developed, implemented and lessons shared. | At least 5 independent budget analyses at national-level conducted and shared by Social Accountability (SA) grantees by June 2015. | Baseline: 0 Target: 5 Data Source:Pro Public Report |
|  | SA media programs targeting entitlements, budget awareness-raising and key PFM issues developed and tested in at least 10 Districts by June 2014. | Baseline: 0 Target: Coverage in 10 Districts Data Source: Media concept notes and programme scripts Focus Group surveys |
|  | Procurement monitoring, expenditure tracking and budget awareness-raising undertaken in at least 90 VDCs by June 2015. | Baseline: o Target: 90 VDCs Data source: Local-level Grantee reports |
|  | At least 10 SA initiatives targeting entitlement programs are completed and the lessons drawn up and disseminated by June 2015. | Baseline: 0 Target: 10 Data source: Project reports, Entitlement program reports |
|  | Grantee Performance Monitoring & Reporting System and SA Learning Strategy developed and operational by end of 2013. | Baseline: 0 Target: Functional system used by project team, grantees and monitoring firm |
| Output 4: Trust Fund Administration and Management MDTF administered and managed effectively. | Program Results Framework with performance indicators submitted to the PCC for their endorsement by June 2013. | Baseline: 0 Target: Approved MDTF Programmatic RF |
|  | MDTF Progress Reporting based on Results Framework Performance Indicators and to include quantitative and qualitative performance assessments by December 2013. | Baseline: 0 Target: Qualitative and quantitative progress reports submitted by December 2013 |
|  | Operational risk assessment (ORA) on PFM completed and submitted to the Program Management by June 2013. | Baseline: 0 Target: Risk report submitted |
|  | MDTF administration and management rated at least satisfactory in the Mid-term Performance Review and End of Program Evaluation. | Baseline: n/a Target: Satisfactory assessment in mid-term review and evaluations |

# Text boxes

What the MDTF, and the sub-projects funded under the MDTF, is responsible and accountable for delivering. Its’ Terms of Reference.

The MDTF is responsible for delivering this result with the commitment & participation of the Government of Nepal. The Intermediate Outcome assumes the GoN changes the way in which it acts and performs. While the MDTF cannot be held accountable for others to change, it can help to facilitate this by delivering responsive Outputs and creating an enabling environment which facilitates use and behavior change.

The Outcome level takes the gains achieved at the Intermediate Outcome level to scale, throughout all Ministries at the National level as well as vertically at the municipal and local levels of Government. 2015 and beyond and alignment with the draft CAS.

What development partners, nations and stakeholders aim to achieve in the long term. 2020 and beyond. Alignment with the Nepal PFMRP.

Output 3:

Mechanisms to engage citizens in PFM reform developed, implemented and lessons shared.

Output 1:

Public Financial Management (PFM)systems and capacities strengthened.

Output 2:

Quality of public sector audits enhanced.

Impact:

A Nepal that is prosperous, peaceful and just.

Outcome:

Government of Nepal demonstrating improved governance, optimizing outputs from public resources and facilitating inclusive and broad-based development at scale.

Intermediate Outcome:

Financial transparency, performance and accountability of Public Financial Management (PFM) improved at National and Local levels in Nepal.

ATTRIBUTION

Output 4:

MDTF administered and managed effectively.

CONTRIBUTION